# Tennessee Tip to Tip — Statewide Build-Out Strategy

Civvix Inc.

September 2026

What it takes to go from four proven counties to a statewide service any jurisdiction can sign up for, delivered quarterly, with business-license and TPP support bundled on top.

## Where this stands today

Four counties run through one config-driven pipeline in two days: Wilson (88k rooftops), Sumner (107k), Rutherford (180k), Davidson (463k). Every one produced a placed rooftop surface, seams measured in feet, a ranked exception queue, a per-county workbench, and a bulletin — from free data, with one calibration against a real coded roster. The statewide layers are already in the warehouse: 473 DOR situs polygons (every code in Tennessee), 345 certified city boundaries, 95 county polygons. Secretary of State entity files for ~75 counties are already in hand. The method is proven; what remains is scale, automation and operations.

## What “tip to tip” consists of

Four assets, each built once, then maintained:

- The statewide surface — every rooftop in Tennessee placed in its DOR polygon, measured to its nearest seam, cross-checked against the Comptroller and 911 layers, and scored. Roughly 3.3 million address points across 95 counties. Refreshed quarterly.

- The business universe — every active for-profit entity (SOS) plus every 911 business label, city roster and permit layer that exists, geocoded to a rooftop. Refreshed quarterly.

- The jurisdiction views — 95 county workbenches and 345 city workbenches cut from the same surface (a city’s view is the same data filtered to its situs code, with both directions shown).

- The operating loop — roster intake, adjudication, correction packets, bulletins, calibration.

## The build, by phase

### Phase 1 — statewide surface (weeks 1–4)

| Task | How | Effort |
| --- | --- | --- |
| Pull NG911 address points + roads for 91 remaining counties | fetch_county.py --live on a machine with internet (GitHub Actions or a $20/mo VM); ~3M points, ~1.5 GB | 1 engineer-week, mostly wall-clock |
| Generate 91 county configs | Script: situs codes and names come straight from the DOR layer; USPS-only places derived automatically (below); city layers discovered by ArcGIS Online search per county | 1 engineer-week |
| Automate the postal-county map | For every Post_City + ZIP pair across all 3M rooftops, the majority county is the postal home county. Replaces every hand-typed list; also produces the multi-county-city exceptions (Goodlettsville, Portland, White House) automatically | 2 days |
| Consolidated-government rules | Only Davidson (Metro) and Moore (Lynchburg-Moore) need situs_merge; Hartsville-Trousdale is the third | 1 day |
| Run all 95; publish 95 free boundary reports | Batch; ~6 hours compute | automatic |

Deliverable: the free tier live for every county — the lead-generation engine.

### Phase 2 — business universe and municipal views (weeks 4–8)

| Task | How |
| --- | --- |
| SOS entity files for all 95 counties as the primary business layer | Already have ~75; obtain the rest through Civvix’s existing SOS channel |
| Discover per-county 911 business labels, city rosters, permit layers | ArcGIS Online search script, reviewed by hand; Hendersonville-style situs rosters are gold when found |
| 345 city workbenches | Same pipeline, --jurisdiction city:8305; shows the city’s coded-vs-measured both ways |
| Parcel join where free (86 Comptroller counties + Davidson, Montgomery, Rutherford) | Adds parcel ID to the evidence packet and +5 to the score |

### Phase 3 — operations (weeks 6–12)

| Task | How |
| --- | --- |
| Scheduled refresh | GitHub Actions cron (weekly signal poll; quarterly bulk); snapshots to S3; catalog in git |
| Roster intake | The workbench’s browser-side join for small jurisdictions; a county-side script for big ones. Never on Civvix infrastructure |
| Adjudication capacity | Calibration says ~0.3% of placed licensed businesses are miscoded. Statewide (~350k active entities) that’s ~1,000–1,500 findings a year at full penetration. One analyst handles that; two at scale |
| Correction packets + letters | Generated from the workbench; county signs and sends |
| Calibration reports | After each jurisdiction’s first roster; published to the client |
| Financial Control relationship | One person owns it; the same three questions (contractor designation, lookback authority, PO Box rule) answered once for everyone |

### Phase 4 — the annual license and TPP check (parallel, from week 8)

The situs surface is also the denominator Civvix has been missing. Every business is now a rooftop with a jurisdiction. That answers, per business:

- Business license — which county and which city should have issued one (T.C.A. § 67-4-708), and whether the clerk’s roster shows it. The SOS entity file against the clerk’s roster, placed on the map, is the discovery product Civvix already sells — now with jurisdiction certainty.

- TPP — which assessor’s roll the personalty belongs on (§ 67-5-502 situs; home-base rule), and whether a schedule was filed. Same placed universe against the assessor’s TPP roll.

One annual run per jurisdiction: placed universe × license roster × TPP roll → three exception lists from one geography. The situs subscription is the quarterly relationship; the annual check is the recovery event. They share every byte of infrastructure.

## What it costs

|  | Year 1 | Ongoing |
| --- | --- | --- |
| Engineering (Marty + one) | the phases above, ~3 engineer-months | 0.5 FTE maintenance |
| Analysts | 1 from month 3 | 2 at 40+ jurisdictions |
| Infrastructure | S3 + a small VM/Actions: under $500/mo at full scale | same |
| Data | $0 for the surface; ~$2–3K one-time reserve for the three or four parcel gaps | $0 recurring |
| Insurance | ~$3–5K/yr (see insurance memo) | same |
| Legal | Tennessee counsel on the § 67-1-1704(e) reuse question and the engagement letter — once | — |

## Sequencing that compounds

Start from the Wilson seam outward. Every county line has two sides, and a finding on one side is a finding on the other: the Lebanon Road / Old Hickory corridor is simultaneously a Wilson and a Davidson matter; Brentwood’s ZIP spilling into south Davidson (7,481 rooftops) is a Davidson and a Williamson matter. Middle Tennessee’s ring — Davidson, Williamson, Rutherford, Wilson, Sumner, Robertson, Cheatham, Maury — is 8 counties, ~1.3M rooftops, and the densest seams in the state. Sign those and the map sells itself to the next ring.

Then the other three metros (Knox, Hamilton, Shelby) — each is one county plus a city with its own open data — then the rest by seam density.

## What “sign up” looks like

- A finance director opens their county’s free boundary report. It shows the seams, the exposure ranking, the State-data conflicts, and the count of named businesses in each class.

- They click “Start monitoring.” Fixed annual fee under the bid threshold (pricing memo). An engagement letter with the data-handling protocol and the client-furnishes-GIS clause.

- They request their situs report through REP (we provide the request; they send it).

- First roster join, adjudicated queue, correction packets — within two weeks of the roster.

- Quarterly thereafter: refresh, re-measure, new/resolved/moved, packets, bulletin.

- Annually: the license and TPP check against the same placed universe.

## What could stop it

- § 67-1-1704(e) reuse across jurisdictions — get counsel’s answer before the second county signs. The public surface is unaffected; the question is only about roster-derived facts.

- Financial Control’s three unanswered questions — one phone call.

- Business universe quality — the SOS file has holding companies and stale addresses; the calibration loop is what keeps this honest, and it should be published to every client.

- Adjudication discipline — the felony exposure is personal. Two or three named people, a written protocol, no shortcuts.